## Cost by Deliverable
[Proposer Name]
QA RFP Cost Sheet – Cost by Deliverable
Deliverables | Frequency** | Cost
Confirm the deliverable review process
Evaluate deliverable content requirements
Confirm the deliverable submission process
Define quality standards and metrics for measuring outputs
Define processes for monitoring and measuring quality outcomes
Develop QA reporting procedures and create reports
Develop methods to ensure Project Management and Executive Management are appropriately alerted to key events or deviations from the Statement of Work
Review the State and Contractors proposed risk mitigation and issue resolution/escalation procedures
Monthly Status Reports
SUB-TOTAL |  | 0
PMO – Evaluation of PMO Contractor Deliverables
1000PMGT-001: Preliminary Project Work Plan
1000PMGT-002: Project Work Plan Updates
1000PMGT-003: Project Vision and Charter
1000PMGT-007: Project Issues and Risks Management Plan
1000PMGT-008: Project Scope and Change Management Plan
1000PMGT-010: Mentoring and Knowledge Transfer Plan
1000PMGT-011: Project Procurement Library
1000PMGT-012: Project Management Standards
1000PMGT-013: Staff Development and Retention Plan
1000PMGT-020: To Be Business Model
1000PMGT-015: Quarterly Status reports
1000PMGT-015: Weekly/Monthly Status reports
1000PMGT-016: Final Status Report
1000PMGT-017: Resource Requirement Assessment
1000PMGT-021:Change Readiness and Communications Plan
1000PMGT-023: Advanced Planning Document Updates | Quarterly
1000PMGT-028: Project Procurement Guides
1000PMGT-030: OneDSS Org Transition Plan
1000PMGT-033: Change Control Documentation | Quarterly
1000PMGT-040: Organization Change Management and Readiness
SUB-TOTAL |  | 0
CAFÉ Deliverables – Evaluation of Implementation Contractor Deliverables
CAFÉ.101.r.v Project work plan and updates, in both electronic and paper form
CAFÉ.103.r.v Project Vision and Charter
CAFÉ.105.r.v Contractor-State Staff Organizational Reporting Relationships & Responsibilities Plan
CAFÉ.106.r.v Project Problem/Issue management plan updates as required | Quarterly review
CAFÉ.107.r.v Project Risk Mitigation management plan updates as required | Quarterly review
CAFÉ.108.r.v Project Scope and Change management plan updates as required | Quarterly review
CAFÉ.109.r.v Project Mentoring and Transition strategy | Quarterly review
CAFÉ.110.r.v Project Deliverable Repository, Control, Standards and Procedures Document | Quarterly review
CAFÉ.112.r.v Staff Development, Retention and Back-up Plan
CAFÉ.113.r.v Project web Site and updates | Quarterly review
CAFÉ.115.r.v Presence Certification Statement of project staff assignment, location and schedule | Quarterly review
CAFÉ.116.r.v Weekly status reports | Monthy Sample
CAFÉ.117.r.v Monthly status reports | Monthly sample
CAFÉ.118.r.v Quarterly status reports | Quarterly review
CAFÉ.119.r.v Action item reports | Monthly review
CAFÉ.120.r.v Final End of Project report.
CAFÉ.202.r.v CAFÉ System Requirements document | 5 releases
CAFÉ.203.r.v Resource Requirements document | 5 releases
CAFÉ.204.r.v Capacity Analysis/System Performance document | 5 releases
CAFÉ.205.r.v Service Level Agreement document
CAFÉ.206.r.v CAFÉ Detail System Design document | 5 releases
CAFÉ.207.r.v CAFÉ Technical Service Oriented Architectural Design document
CAFÉ.208.r.v Communications, Notifications and Forms document | 5 releases
CAFÉ.209.r.v Report Layouts, Design and Specifications document | 5 releases
CAFÉ.210.r.v Data Dictionary/Data Mapping document | 5 releases
CAFÉ.212.r.v Business Continuity and Disaster Recovery plan
CAFÉ.213.r.v Case Workflow and Procedural specifications | 5 releases
CAFÉ.214.r.v Security and Auditing plan
CAFÉ.215.r.v Vulnerability/Intrusion Detection plan
CAFÉ.302.r.v Volumetric documentation and results of application tuning or environmental adjustments | 5 releases
CAFÉ.303.r.v System test plan | 5 releases
CAFÉ.306.r.v All updated models (i.e. Use Case, Object, Data, Security etc.) | 5 releases
CAFÉ.307.r.v Requirements Traceability Matrix | 5 releases
CAFÉ.308.r.v System Test Scripts, Scenarios, Cases, Data Pools (automated and manual) | 5 releases
CAFÉ.309.r.v Unit test results document | 5 releases
CAFÉ.310.r.v User documentation | 5 releases
CAFÉ.311.r.v Operations documentation | 5 releases
CAFÉ.312.r.v System documentation | 5 releases
CAFÉ.313.r.v System test results document including security, audit, vulnerability and intrusion detection | 5 releases
CAFÉ.314.r.v System testing certification letter | 5 releases
CAFÉ.402.r.v Transfer to State of system test scripts and automated testing packages | 5 releases
CAFÉ.403.r.v Structured sets of test data, including converted production data and longitudinal testing | 5 releases
CAFÉ.404.r.v Defect Corrections report | 5 releases
CAFÉ.405.r.v Integration and Outcomes report | 5 releases
CAFÉ.406.r.v Adequacy of training materials and system documentation report | 5 releases
CAFÉ.407.r.v System back-out, backup and recovery report | 5 releases
CAFÉ.408.r.v System fail-over, backup and recovery report | 5 releases
CAFÉ.501.r.v Survey of staff, citizens and providers to ascertain perceptions pre-implementation
CAFÉ.502.r.v Analysis, Findings and Recommendations related to staff readiness | 5 releases
CAFÉ.503.r.v Change Readiness Plan
CAFÉ.504.r.v Communications Plan
CAFÉ.505.r.v Change Readiness Campaign Material | 5 releases
CAFÉ.506.r.v Business Process Change Document | 5 releases
CAFÉ.507.r.v Survey and analysis of staff, customers and providers to ascertain perceptions post implementation.
CAFÉ.601.r.v Training plan and updates for the CAFÉ System | 5 releases
CAFÉ.602.r.v CBT modules | 5 releases
CAFÉ.603.r.v CBT software training on creation, cataloging and maintenance of modules;
CAFÉ.606.r.v Digital Recordings of Training Sessions set up for user access as a webinar | 5 releases
CAFÉ.609.r.v Training Feedback survey instruments | 5 releases
CAFÉ.610.r.v Training Feedback analysis | 5 releases
CAFÉ.611.r.v Integration of CAFÉ training into ongoing New Worker Orientation and training curriculum | 5 releases
CAFÉ.701.r.v Conversion plan | 5 releases
CAFÉ.702.r.v Conversion specification document | 5 releases
CAFÉ.703.r.v Data purification/transformation strategy document | 5 releases
CAFÉ.704.r.v Data clean-up lists and results | 5 releases
CAFÉ.705.r.v Conversion test plans | 5 releases
CAFÉ.706.r.v Conversion programs and documentation | 5 releases
CAFÉ.707.r.v Conversion software test results document | 5 releases
CAFÉ.708.r.v Conversion test results reports | 5 releases
CAFÉ.801.r.v Pilot test plan | 5 releases
CAFÉ.802.r.v Pilot testing readiness certification letter | 5 releases
CAFÉ.803.r.v Pilot test completion certification letter | 5 releases
CAFÉ.804.r.v Capacity simulations, tuning and benchmark reports | 5 releases
CAFÉ.805.r.v Written responses to defects, discrepancies and issues identified during pilot testing | 5 releases
CAFÉ.806.r.v Pilot operations reports | 5 releases
CAFÉ.807.r.v Implemented CAFÉ System Help Desk procedures | 5 releases
CAFÉ.901.r.v Statewide incremental implementation deployment plan | 5 releases
CAFÉ.902.r.v Statewide "go-live" checklist | 5 releases
CAFÉ.903.r.v Statewide Implementation Readiness Assessment Certification letter | 5 releases
CAFÉ.904.r.v Help Desk detail and management summary reports | 5 releases
CAFÉ.905.r.v Procedures for reporting problems and escalation procedures | 5 releases
CAFÉ.906.r.v Compilation and Posting of Implementation Q&A | 5 releases
CAFÉ.908.r.v Release and Site implementation letters | 5 releases
CAFÉ.909.r.v Implementation report | 5 releases
CAFÉ.909.r.v Final Implementation report
CAFÉ.910.r.v Certification of state acceptance document | 5 releases
CAFÉ.1001.r.v All CAFÉ System documentation
CAFÉ.1002.r.v All updated source code and models
CAFÉ.1003.r.v Inventory and turnover of all work in progress
CAFÉ.1004.r.v Inventory and turnover of any equipment, software and licenses
CAFÉ.1005.r.v Status of any outstanding problems and recommendations for system enhancements
CAFÉ.1006.r.v Status and critique of system changes performed by State Staff post-implementation
CAFÉ.1007.r.v System turnover plan | 5 releases
CAFÉ.1007.r.v Final system turnover plan
CAFÉ.1008.r.v Turnover results report | 5 releases
CAFÉ.1101.r.v All necessary system documentation and support necessary to obtain federal approval | 5 releases
CAFÉ.1102.r.v Plan for correcting system deficiencies identified as a result of federal review
SUB-TOTAL |  | 0
Document Management and Imaging Deliverables – Evaluation of Implementation Contractor Deliverables
Deliverable 1: Detailed Project Plan | Weekly
Deliverable 2: Deliverable Document Templates
Deliverable 3: Communication Plan
Deliverable 4: Requirements Specifications Document (RSD)
Deliverable 5: Operational Plan | 3 releases
Deliverable 6: Security Plan
Deliverable 7: Design Specifications Document (DSD) | 3 releases
Deliverable 8: Test Plan - Unit, System, UAT | 3 releases
Deliverable 9: Training Plan | 3 releases
Deliverable 10: Conversion/Integration Plan
Deliverable 11: Implementation Plan | 3 releases
Deliverable 12: Disaster Recovery Plan
Deliverable 13: System Test Results | 3 releases
Deliverable 14: User Acceptance Test (UAT) Results | 3 releases
Deliverable 15: Support Plan
Deliverable 16: Transition Plan
Deliverable 17: Acceptance in Production of Delivered Modules | 3 releases
SUB-TOTAL |  | 0
Customer Service Center(CSC) – Evaluation of Implementation Contractor Deliverables – Deliverables have not been finalized for this procurement. Actual deliverables will be specified in subsequent contract negotiations once the deliverables have been finalized. Anticipate 2-3 implementations occurring after QA contractor's begin date.
Project work plan and updates, in both electronic and paper form
Contractor-State Staff Organizational Reporting Relationships & Responsibilities Plan
Project Problem/Issue management plan updates as required | Quarterly review
Project Scope and Change management plan updates as required | Quarterly review
Project Mentoring and Transition strategy | Quarterly review
Staff Development, Retention and Back-up Plan
Weekly status reports | Monthly sample
Monthly status reports | Monthly sample
Quarterly status reports | Quarterly
Action item reports | Monthly review
Final End of Project report.
System Requirements document
Resource Requirements document
Capacity Analysis/System Performance document
CSC Detail System Design document
Report Layouts, Design and Specifications document
Business Continuity and Disaster Recovery plan
Case Workflow and Procedural specifications
CSC System test plan
All updated models (i.e. Use Case, Object, Data, Security etc.)
CSC Requirements Traceability Matrix
CSC System Test Scripts, Scenarios, Cases, Data Pools (automated and manual)
CSC IVR Scripts by Program and Call Type
CSC Unit test results document
CSC User documentation
CSC Operations documentation
CSC System documentation
CSC Transfer to State of system test scripts and automated testing packages
CSC Structured sets of test data, including converted production data and longitudinal testing
CSC Defect Corrections report
CSC Adequacy of training materials and system documentation report
CSC System back-out, backup and recovery report
CSC System fail-over, backup and recovery report
CSC Analysis, Findings and Recommendations related to staff readiness
CSC Survey and analysis of staff, customers and providers to ascertain perceptions post implementation.
CSC Training plan and updates for the CSC System
CSC CBT modules
CSC software training on creation, cataloging and maintenance of modules;
CSC Digital Recordings of Training Sessions set up for user access as a webinar
CSC Training Feedback survey instruments
CSC Training Feedback analysis
CSC Pilot test plan
CSC Pilot testing readiness certification letter
CSC Capacity simulations, tuning and benchmark reports
CSC Written responses to defects, discrepancies and issues identified during pilot testing
CSC Pilot operations reports
CSC Statewide incremental implementation deployment plan
CSC Statewide "go-live" checklist
CSC Help Desk detail and management summary reports
CSC Compilation and Posting of Implementation Q&A
CSC Implementation report
CSC Final Implementation report
All CSC System documentation
CSC Inventory and turnover of all work in progress
CSC Inventory and turnover of any equipment, software and licenses
CSC status of any outstanding problems and recommendations for system enhancements
CSC status and critique of system changes performed by State Staff post-implementation
CSC System turnover plan
CSC final system turnover plan
CSC turnover results report
CSC Plan for correcting system deficiencies identified as a result of federal review
SUB-TOTAL |  | 0
SACWIS – Evaluation of Implementation Contractor Deliverables – Though this is a future procurement, anticipated deliverables with an assumption of 3 phases is the basis for estimating the cost for this project from a QA perspective. Actual deliverables and phases will be specified in subsequent contract negotiations, once the SACWIS RFP has been published in final form.
Project work plan and updates, in both electronic and paper form
Contractor-State Staff Organizational Reporting Relationships & Responsibilities Plan
Project Problem/Issue management plan updates as required | Quarterly review
Project Scope and Change management plan updates as required | Quarterly review
Project Mentoring and Transition strategy | Quarterly review
Staff Development, Retention and Back-up Plan
Presence Certification Statement of project staff assignment, location and schedule | Quarterly review
Weekly status reports | Monthly sample
Monthly status reports | Monthly sample
Quarterly status reports | Quarterly
Action item reports | Monthly review
Final End of Project report.
System Requirements document | 6 revisions
Resource Requirements document | 6 revisions
Capacity Analysis/System Performance document | 3 revisions
SACWIS Detail System Design document | 3 revisions
SACWIS Technical Service Oriented Architectural Design document
Report Layouts, Design and Specifications document | 3 revisions
Data Dictionary/Data Mapping document | 3 revisions
Business Continuity and Disaster Recovery plan
Case Workflow and Procedural specifications | 3 revisions
Volumetric documentation and results of application tuning or environmental adjustments | 3 releases
SACWIS System test plan | 3 releases
SACWIS Requirements Traceability Matrix | 3 releases
SACWIS System Test Scripts, Scenarios, Cases, Data Pools (automated and manual) | 3 releases
SACWIS Unit test results document | 3 releases
SACWIS User documentation | 3 releases
SACWIS Operations documentation | 3 releases
SACWIS System documentation | 3 releases
SACWIS System testing certification letter | 3 releases
SACWIS Transfer to State of system test scripts and automated testing packages | 3 releases
SACWIS Structured sets of test data, including converted production data and longitudinal testing | 3 releases
SACWIS Defect Corrections report | 3 releases
SACWIS Integration and Outcomes report | 3 releases
SACWIS Adequacy of training materials and system documentation report | 3 releases
SACWIS System back-out, backup and recovery report | 3 releases
SACWIS System fail-over, backup and recovery report | 3 releases
SACWIS Survey of staff, citizens and providers to ascertain perceptions pre-implementation
SACWIS Analysis, Findings and Recommendations related to staff readiness | 3 releases
SACWIS Business Process Change Document | 3 releases
SACWIS Survey and analysis of staff, customers and providers to ascertain perceptions post implementation.
SACWIS Training plan and updates for the SACWIS System | 3 releases
SACWIS CBT modules | 3 releases
SACWIS software training on creation, cataloging and maintenance of modules;
SACWIS Digital Recordings of Training Sessions set up for user access as a webinar | 3 releases
SACWIS Training Feedback survey instruments | 3 releases
SACWIS Training Feedback analysis | 3 releases
SACWIS Integration of SACWIS training into ongoing New Worker Orientation and training curriculum | 3 releases
SACWIS Conversion plan | 3 releases
SACWIS Conversion specification document | 3 releases
SACWIS Data purification/transformation strategy document | 3 releases
SACWIS Data clean-up lists and results | 3 releases
SACWIS Conversion test plans | 3 releases
SACWIS Conversion programs and documentation | 3 releases
SACWIS Conversion software test results document | 3 releases
SACWIS Conversion test results reports | 3 releases
SACWIS Pilot test plan | 3 releases
SACWIS Pilot testing readiness certification letter | 3 releases
SACWIS Pilot test completion certification letter | 3 releases
SACWIS Capacity simulations, tuning and benchmark reports | 3 releases
SACWIS Written responses to defects, discrepancies and issues identified during pilot testing | 3 releases
SACWIS Pilot operations reports | 3 releases
SACWIS Statewide incremental implementation deployment plan | 3 releases
SACWIS Statewide "go-live" checklist | 3 releases
SACWIS Statewide Implementation Readiness Assessment Certification letter | 3 releases
SACWIS Help Desk detail and management summary reports | 3 releases
SACWIS Compilation and Posting of Implementation Q&A | 3 releases
SACWIS Release and Site implementation letters | 3 releases
SACWIS Implementation report | 3 releases
SACWIS Final Implementation report
SACWIS Certification of state acceptance document | 3 releases
All SACWIS System documentation
All updated SACWIS source code and models
SACWIS Inventory and turnover of all work in progress
SACWIS Inventory and turnover of any equipment, software and licenses
SACWIS status of any outstanding problems and recommendations for system enhancements
SACWIS status and critique of system changes performed by State Staff post-implementation
SACWIS System turnover plan | 3 releases
SACWIS final system turnover plan
SACWIS turnover results report | 3 releases
SACWIS Plan for correcting system deficiencies identified as a result of federal review
SUB-TOTAL |  | 0
TOTAL FOR ALL DELIVERABLES |  | 0
** Please note the following in respect to Frequency: • Quarterly –The deliverable is due quarterly, and that each deliverable is reviewed. • Monthly sample – The deliverable is due weekly or monthly, but monthly sampling of the deliverable is conducted. • No value – The deliverable is reviewed in a single iteration. • N revisions – The deliverable is reviewed for each of N phases. Assume that the cost of subsequent phases is 30% of the initial review of the deliverable.

## Staff Hourly Rate
[Proposer Name]
QA RFP Cost Sheet – Cost by Task
Position Title | Avg Cost/Position | # | Total Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total |  | 0 | 0

## Miscellaneous Items
[Proposer Name]
QA RFP Cost Sheet – Miscellaneous Items
Item Description | Justification* | Avg. Cost/Item | # | Total Cost
0
0
0
0
0
0
0
0
0
0
Total |  |  |  | 0
* The Justification should describe why the item is necessary

## Required State Resources
[Proposer Name]
QA RFP Cost Sheet – Required State Resources
Item Description | Justification* | Avg. Cost/Item | # | Total Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total |  |  |  | 0
* The Justification should describe why the item is necessary as well as why it should be provided as a State Resource